## Tech Projects
Project | Business Sector | Budget ($) | Percent Completion | Budget Spent/ Actual Cost ($) | Time Elapsed (months) | Planned Duration (months) | Planned Value | Earned Value | Cost Vairance (CV) | Cost Performance Index | Schedule Variance | Schedule Performance Index | Budget Status | Schedule Status | Completion Status | To-Complete Performance Index
Project 1 | E-Commerce | 120000 | 0.47 | 16998 | 8 | 18 | 53333.3333 | 56400 | 39402 | 3.318 | 3066.6667 | 1.0575 | Under Budget | Ahead of Schedule | In Progress | 0.61746
Project 2 | Clean Energy | 250000 | 1 | 90225 | 13 | 20 | 162500 | 250000 | 159775 | 2.7709 | 87500 | 1.5385 | Under Budget | Ahead of Schedule | Complete | 0
Project 3 | EdTech | 80000 | 0.58 | 5206 | 9 | 14 | 51428.5714 | 46400 | 41194 | 8.9128 | -5028.5714 | 0.90222 | Under Budget | Behind Schedule | In Progress | 0.44923
Project 4 | Healthcare IT | 300000 | 0.69 | 19154 | 1 | 20 | 15000 | 207000 | 187846 | 10.8071 | 192000 | 13.8 | Under Budget | Ahead of Schedule | In Progress | 0.33114
Project 5 | FinTech | 150000 | 0.78 | 66979 | 9 | 12 | 112500 | 117000 | 50021 | 1.7468 | 4500 | 1.04 | Under Budget | Ahead of Schedule | In Progress | 0.39749
Project 6 | E-Commerce | 500000 | 0.24 | 490443 | 14 | 20 | 350000 | 120000 | -370443 | 0.24468 | -230000 | 0.34286 | Over Budget | Behind Schedule | In Progress | 39.7614
Project 7 | EdTech | 90000 | 1 | 17399 | 10 | 14 | 64285.7143 | 90000 | 72601 | 5.1727 | 25714.2857 | 1.4 | Under Budget | Ahead of Schedule | Complete | 0
Project 8 | Healthcare IT | 220000 | 0.65 | 4440 | 1 | 15 | 14666.6667 | 143000 | 138560 | 32.2072 | 128333.3333 | 9.75 | Under Budget | Ahead of Schedule | In Progress | 0.35721
Project 9 | Enterprise Software | 400000 | 0.2 | 383135 | 3 | 20 | 60000 | 80000 | -303135 | 0.2088 | 20000 | 1.3333 | Over Budget | Ahead of Schedule | In Progress | 18.9742
Project 10 | GovTech | 75000 | 0.49 | 73383 | 1 | 12 | 6250 | 36750 | -36633 | 0.5008 | 30500 | 5.88 | Over Budget | Ahead of Schedule | In Progress | 23.6549
Project 11 | Healthcare IT | 600000 | 0.05 | 436189 | 3 | 20 | 90000 | 30000 | -406189 | 0.068778 | -60000 | 0.33333 | Over Budget | Behind Schedule | In Progress | 3.4796
Project 12 | GovTech | 130000 | 0.98 | 44 | 9 | 12 | 97500 | 127400 | 127356 | 2895.4545 | 29900 | 1.3067 | Under Budget | Ahead of Schedule | In Progress | 0.020007
Project 13 | Enterprise Software | 270000 | 0.6 | 254155 | 15 | 20 | 202500 | 162000 | -92155 | 0.63741 | -40500 | 0.8 | Over Budget | Behind Schedule | In Progress | 6.816
Project 14 | EdTech | 95000 | 0.27 | 4322 | 8 | 12 | 63333.3333 | 25650 | 21328 | 5.9348 | -37683.3333 | 0.405 | Under Budget | Behind Schedule | In Progress | 0.76479
Project 15 | Cybersecurity | 800000 | 0.69 | 394088 | 2 | 20 | 80000 | 552000 | 157912 | 1.4007 | 472000 | 6.9 | Under Budget | Ahead of Schedule | In Progress | 0.61097
Project 16 | Cybersecurity | 180000 | 0.52 | 35748 | 6 | 12 | 90000 | 93600 | 57852 | 2.6183 | 3600 | 1.04 | Under Budget | Ahead of Schedule | In Progress | 0.59895
Project 17 | GovTech | 350000 | 0.37 | 195574 | 6 | 20 | 105000 | 129500 | -66074 | 0.66215 | 24500 | 1.2333 | Over Budget | Ahead of Schedule | In Progress | 1.4279
Project 18 | E-Commerce | 110000 | 0.17 | 93391 | 11 | 12 | 100833.3333 | 18700 | -74691 | 0.20023 | -82133.3333 | 0.18545 | Over Budget | Behind Schedule | In Progress | 5.497
Project 19 | Healthcare IT | 1000000 | 0.27 | 740328 | 19 | 20 | 950000 | 270000 | -470328 | 0.3647 | -680000 | 0.28421 | Over Budget | Behind Schedule | In Progress | 2.8112
Project 20 | GovTech | 60000 | 0.34 | 20780 | 5 | 6 | 50000 | 20400 | -380 | 0.98171 | -29600 | 0.408 | Over Budget | Behind Schedule | In Progress | 1.0097
Project 21 | Cybersecurity | 120000 | 0.79 | 5228 | 18 | 18 | 120000 | 94800 | 89572 | 18.1331 | -25200 | 0.79 | Under Budget | Behind Schedule | In Progress | 0.21957
Project 22 | Healthcare IT | 250000 | 0.07 | 169471 | 18 | 20 | 225000 | 17500 | -151971 | 0.10326 | -207500 | 0.077778 | Over Budget | Behind Schedule | In Progress | 2.8872
Project 23 | FinTech | 80000 | 0.05 | 18720 | 6 | 14 | 34285.7143 | 4000 | -14720 | 0.21368 | -30285.7143 | 0.11667 | Over Budget | Behind Schedule | In Progress | 1.2402
Project 24 | Enterprise Software | 300000 | 0.26 | 74449 | 4 | 20 | 60000 | 78000 | 3551 | 1.0477 | 18000 | 1.3 | Under Budget | Ahead of Schedule | In Progress | 0.98426
Project 25 | EdTech | 150000 | 0.46 | 25493 | 12 | 12 | 150000 | 69000 | 43507 | 2.7066 | -81000 | 0.46 | Under Budget | Behind Schedule | In Progress | 0.65057
Project 26 | Artificial Intelligence | 500000 | 0.18 | 360640 | 15 | 20 | 375000 | 90000 | -270640 | 0.24956 | -285000 | 0.24 | Over Budget | Behind Schedule | In Progress | 2.942
Project 27 | EdTech | 90000 | 0.72 | 24797 | 3 | 14 | 19285.7143 | 64800 | 40003 | 2.6132 | 45514.2857 | 3.36 | Under Budget | Ahead of Schedule | In Progress | 0.38649
Project 28 | Enterprise Software | 220000 | 0.17 | 138343 | 7 | 15 | 102666.6667 | 37400 | -100943 | 0.27034 | -65266.6667 | 0.36429 | Over Budget | Behind Schedule | In Progress | 2.2362
Project 29 | FinTech | 400000 | 0.57 | 25815 | 9 | 20 | 180000 | 228000 | 202185 | 8.8321 | 48000 | 1.2667 | Under Budget | Ahead of Schedule | In Progress | 0.45967
Project 30 | FinTech | 75000 | 0.59 | 43768 | 3 | 12 | 18750 | 44250 | 482 | 1.011 | 25500 | 2.36 | Under Budget | Ahead of Schedule | In Progress | 0.98457
Project 31 | EdTech | 600000 | 0.47 | 581579 | 6 | 20 | 180000 | 282000 | -299579 | 0.48489 | 102000 | 1.5667 | Over Budget | Ahead of Schedule | In Progress | 17.2629
Project 32 | Telecommunications | 130000 | 0.26 | 34889 | 3 | 12 | 32500 | 33800 | -1089 | 0.96879 | 1300 | 1.04 | Over Budget | Ahead of Schedule | In Progress | 1.0114
Project 33 | Cybersecurity | 270000 | 0.7 | 251600 | 9 | 20 | 121500 | 189000 | -62600 | 0.75119 | 67500 | 1.5556 | Over Budget | Ahead of Schedule | In Progress | 4.4022
Project 34 | Artificial Intelligence | 95000 | 0.37 | 19523 | 5 | 12 | 39583.3333 | 35150 | 15627 | 1.8004 | -4433.3333 | 0.888 | Under Budget | Behind Schedule | In Progress | 0.79296
Project 35 | Telecommunications | 800000 | 0.34 | 558627 | 6 | 20 | 240000 | 272000 | -286627 | 0.48691 | 32000 | 1.1333 | Over Budget | Ahead of Schedule | In Progress | 2.1875
Project 36 | Telecommunications | 180000 | 0.21 | 131722 | 11 | 12 | 165000 | 37800 | -93922 | 0.28697 | -127200 | 0.22909 | Over Budget | Behind Schedule | In Progress | 2.9454
Project 37 | GovTech | 350000 | 0.52 | 112751 | 2 | 20 | 35000 | 182000 | 69249 | 1.6142 | 147000 | 5.2 | Under Budget | Ahead of Schedule | In Progress | 0.70812
Project 38 | EdTech | 110000 | 0.51 | 77587 | 9 | 12 | 82500 | 56100 | -21487 | 0.72306 | -26400 | 0.68 | Over Budget | Behind Schedule | In Progress | 1.6629
Project 39 | Clean Energy | 1000000 | 0.34 | 478958 | 19 | 20 | 950000 | 340000 | -138958 | 0.70987 | -610000 | 0.35789 | Over Budget | Behind Schedule | In Progress | 1.2667
Project 40 | Enterprise Software | 60000 | 0.59 | 36600 | 5 | 6 | 50000 | 35400 | -1200 | 0.96721 | -14600 | 0.708 | Over Budget | Behind Schedule | In Progress | 1.0513
Project 41 | GovTech | 120000 | 0.23 | 18749 | 9 | 18 | 60000 | 27600 | 8851 | 1.4721 | -32400 | 0.46 | Under Budget | Behind Schedule | In Progress | 0.91258
Project 42 | GovTech | 250000 | 0.96 | 194978 | 1 | 20 | 12500 | 240000 | 45022 | 1.2309 | 227500 | 19.2 | Under Budget | Ahead of Schedule | In Progress | 0.18175
Project 43 | Telecommunications | 80000 | 0.84 | 47229 | 3 | 14 | 17142.8571 | 67200 | 19971 | 1.4229 | 50057.1429 | 3.92 | Under Budget | Ahead of Schedule | In Progress | 0.39059
Project 44 | Healthcare IT | 300000 | 0.52 | 24208 | 6 | 20 | 90000 | 156000 | 131792 | 6.4442 | 66000 | 1.7333 | Under Budget | Ahead of Schedule | In Progress | 0.52213
Project 45 | Artificial Intelligence | 150000 | 0.68 | 126073 | 8 | 12 | 100000 | 102000 | -24073 | 0.80906 | 2000 | 1.02 | Over Budget | Ahead of Schedule | In Progress | 2.0061
Project 46 | GovTech | 500000 | 0.37 | 106462 | 4 | 20 | 100000 | 185000 | 78538 | 1.7377 | 85000 | 1.85 | Under Budget | Ahead of Schedule | In Progress | 0.80043
Project 47 | EdTech | 90000 | 0.92 | 56790 | 12 | 14 | 77142.8571 | 82800 | 26010 | 1.458 | 5657.1429 | 1.0733 | Under Budget | Ahead of Schedule | In Progress | 0.2168
Project 48 | Artificial Intelligence | 220000 | 0.08 | 169402 | 9 | 15 | 132000 | 17600 | -151802 | 0.10389 | -114400 | 0.13333 | Over Budget | Behind Schedule | In Progress | 4.0002
Project 49 | E-Commerce | 400000 | 0.48 | 181672 | 6 | 20 | 120000 | 192000 | 10328 | 1.0568 | 72000 | 1.6 | Under Budget | Ahead of Schedule | In Progress | 0.9527
Project 50 | GovTech | 75000 | 0.34 | 54436 | 10 | 12 | 62500 | 25500 | -28936 | 0.46844 | -37000 | 0.408 | Over Budget | Behind Schedule | In Progress | 2.4071
Project 51 | GovTech | 600000 | 0.88 | 568514 | 3 | 20 | 90000 | 528000 | -40514 | 0.92874 | 438000 | 5.8667 | Over Budget | Ahead of Schedule | In Progress | 2.2867
Project 52 | Telecommunications | 130000 | 0.78 | 45571 | 2 | 12 | 21666.6667 | 101400 | 55829 | 2.2251 | 79733.3333 | 4.68 | Under Budget | Ahead of Schedule | In Progress | 0.33875
Project 53 | Clean Energy | 270000 | 0.64 | 46660 | 15 | 20 | 202500 | 172800 | 126140 | 3.7034 | -29700 | 0.85333 | Under Budget | Behind Schedule | In Progress | 0.43521
Project 54 | Cybersecurity | 95000 | 0.31 | 83295 | 9 | 12 | 71250 | 29450 | -53845 | 0.35356 | -41800 | 0.41333 | Over Budget | Behind Schedule | In Progress | 5.6002
Project 55 | Healthcare IT | 800000 | 0.15 | 160274 | 10 | 20 | 400000 | 120000 | -40274 | 0.74872 | -280000 | 0.3 | Over Budget | Behind Schedule | In Progress | 1.063
Project 56 | EdTech | 180000 | 0.7 | 8355 | 12 | 12 | 180000 | 126000 | 117645 | 15.0808 | -54000 | 0.7 | Under Budget | Behind Schedule | In Progress | 0.3146
Project 57 | E-Commerce | 350000 | 0.54 | 280659 | 13 | 20 | 227500 | 189000 | -91659 | 0.67342 | -38500 | 0.83077 | Over Budget | Behind Schedule | In Progress | 2.3219
Project 58 | Enterprise Software | 110000 | 0.37 | 106069 | 1 | 12 | 9166.6667 | 40700 | -65369 | 0.38371 | 31533.3333 | 4.44 | Over Budget | Ahead of Schedule | In Progress | 17.6291
Project 59 | EdTech | 1000000 | 0.42 | 683823 | 13 | 20 | 650000 | 420000 | -263823 | 0.61419 | -230000 | 0.64615 | Over Budget | Behind Schedule | In Progress | 1.8344
Project 60 | FinTech | 60000 | 0.28 | 13950 | 1 | 6 | 10000 | 16800 | 2850 | 1.2043 | 6800 | 1.68 | Under Budget | Ahead of Schedule | In Progress | 0.93811
Project 61 | Clean Energy | 120000 | 0.68 | 64754 | 16 | 18 | 106666.6667 | 81600 | 16846 | 1.2602 | -25066.6667 | 0.765 | Under Budget | Behind Schedule | In Progress | 0.69507
Project 62 | Healthcare IT | 250000 | 0.87 | 230808 | 10 | 20 | 125000 | 217500 | -13308 | 0.94234 | 92500 | 1.74 | Over Budget | Ahead of Schedule | In Progress | 1.6934
Project 63 | EdTech | 80000 | 0.97 | 72213 | 14 | 14 | 80000 | 77600 | 5387 | 1.0746 | -2400 | 0.97 | Under Budget | Behind Schedule | In Progress | 0.30821
Project 64 | EdTech | 300000 | 0.58 | 183929 | 19 | 20 | 285000 | 174000 | -9929 | 0.94602 | -111000 | 0.61053 | Over Budget | Behind Schedule | In Progress | 1.0855
Project 65 | Clean Energy | 150000 | 0.52 | 129187 | 8 | 12 | 100000 | 78000 | -51187 | 0.60378 | -22000 | 0.78 | Over Budget | Behind Schedule | In Progress | 3.4594
Project 66 | Cybersecurity | 500000 | 0.85 | 8340 | 18 | 20 | 450000 | 425000 | 416660 | 50.9592 | -25000 | 0.94444 | Under Budget | Behind Schedule | In Progress | 0.15254
Project 67 | GovTech | 90000 | 0.9 | 73882 | 14 | 14 | 90000 | 81000 | 7118 | 1.0963 | -9000 | 0.9 | Under Budget | Behind Schedule | In Progress | 0.55838
Project 68 | EdTech | 220000 | 0.42 | 9751 | 5 | 15 | 73333.3333 | 92400 | 82649 | 9.476 | 19066.6667 | 1.26 | Under Budget | Ahead of Schedule | In Progress | 0.6069
Project 69 | Healthcare IT | 400000 | 0.95 | 289202 | 6 | 20 | 120000 | 380000 | 90798 | 1.314 | 260000 | 3.1667 | Under Budget | Ahead of Schedule | In Progress | 0.18051
Project 70 | E-Commerce | 75000 | 0.7 | 53905 | 4 | 12 | 25000 | 52500 | -1405 | 0.97394 | 27500 | 2.1 | Over Budget | Ahead of Schedule | In Progress | 1.0666
Project 71 | GovTech | 600000 | 0.85 | 87877 | 3 | 20 | 90000 | 510000 | 422123 | 5.8036 | 420000 | 5.6667 | Under Budget | Ahead of Schedule | In Progress | 0.17574
Project 72 | Clean Energy | 130000 | 0.98 | 120205 | 6 | 12 | 65000 | 127400 | 7195 | 1.0599 | 62400 | 1.96 | Under Budget | Ahead of Schedule | In Progress | 0.26544
Project 73 | Cybersecurity | 270000 | 0.25 | 32697 | 9 | 20 | 121500 | 67500 | 34803 | 2.0644 | -54000 | 0.55556 | Under Budget | Behind Schedule | In Progress | 0.85334
Project 74 | FinTech | 95000 | 0.23 | 53417 | 2 | 12 | 15833.3333 | 21850 | -31567 | 0.40905 | 6016.6667 | 1.38 | Over Budget | Ahead of Schedule | In Progress | 1.7591
Project 75 | Artificial Intelligence | 800000 | 0.14 | 793139 | 4 | 20 | 160000 | 112000 | -681139 | 0.14121 | -48000 | 0.7 | Over Budget | Behind Schedule | In Progress | 100.2769
Project 76 | Clean Energy | 180000 | 0.69 | 39579 | 4 | 12 | 60000 | 124200 | 84621 | 3.138 | 64200 | 2.07 | Under Budget | Ahead of Schedule | In Progress | 0.39738
Project 77 | EdTech | 350000 | 0.33 | 143153 | 8 | 20 | 140000 | 115500 | -27653 | 0.80683 | -24500 | 0.825 | Over Budget | Behind Schedule | In Progress | 1.1337
Project 78 | FinTech | 110000 | 0.22 | 96924 | 3 | 12 | 27500 | 24200 | -72724 | 0.24968 | -3300 | 0.88 | Over Budget | Behind Schedule | In Progress | 6.5616
Project 79 | Enterprise Software | 1000000 | 0.52 | 257447 | 5 | 20 | 250000 | 520000 | 262553 | 2.0198 | 270000 | 2.08 | Under Budget | Ahead of Schedule | In Progress | 0.64642
Project 80 | Clean Energy | 60000 | 0.85 | 36701 | 1 | 6 | 10000 | 51000 | 14299 | 1.3896 | 41000 | 5.1 | Under Budget | Ahead of Schedule | In Progress | 0.38628
Project 81 | Clean Energy | 120000 | 0.83 | 81097 | 12 | 18 | 80000 | 99600 | 18503 | 1.2282 | 19600 | 1.245 | Under Budget | Ahead of Schedule | In Progress | 0.52438
Project 82 | EdTech | 250000 | 0.61 | 78724 | 13 | 20 | 162500 | 152500 | 73776 | 1.9371 | -10000 | 0.93846 | Under Budget | Behind Schedule | In Progress | 0.56926
Project 83 | EdTech | 80000 | 0.92 | 10823 | 1 | 14 | 5714.2857 | 73600 | 62777 | 6.8003 | 67885.7143 | 12.88 | Under Budget | Ahead of Schedule | In Progress | 0.092516
Project 84 | FinTech | 300000 | 0.37 | 288793 | 17 | 20 | 255000 | 111000 | -177793 | 0.38436 | -144000 | 0.43529 | Over Budget | Behind Schedule | In Progress | 16.8645
Project 85 | GovTech | 150000 | 0.3 | 137857 | 5 | 12 | 62500 | 45000 | -92857 | 0.32643 | -17500 | 0.72 | Over Budget | Behind Schedule | In Progress | 8.647
Project 86 | E-Commerce | 500000 | 0.56 | 332597 | 17 | 20 | 425000 | 280000 | -52597 | 0.84186 | -145000 | 0.65882 | Over Budget | Behind Schedule | In Progress | 1.3142
Project 87 | Cybersecurity | 90000 | 0.06 | 16110 | 11 | 14 | 70714.2857 | 5400 | -10710 | 0.3352 | -65314.2857 | 0.076364 | Over Budget | Behind Schedule | In Progress | 1.1449
Project 88 | FinTech | 220000 | 0.84 | 60826 | 5 | 15 | 73333.3333 | 184800 | 123974 | 3.0382 | 111466.6667 | 2.52 | Under Budget | Ahead of Schedule | In Progress | 0.22114
Project 89 | FinTech | 400000 | 0.71 | 282982 | 4 | 20 | 80000 | 284000 | 1018 | 1.0036 | 204000 | 3.55 | Under Budget | Ahead of Schedule | In Progress | 0.9913
Project 90 | Telecommunications | 75000 | 0.49 | 14384 | 4 | 12 | 25000 | 36750 | 22366 | 2.5549 | 11750 | 1.47 | Under Budget | Ahead of Schedule | In Progress | 0.63102
Project 91 | Telecommunications | 600000 | 0.75 | 310719 | 16 | 20 | 480000 | 450000 | 139281 | 1.4483 | -30000 | 0.9375 | Under Budget | Behind Schedule | In Progress | 0.51853
Project 92 | E-Commerce | 130000 | 0.51 | 77808 | 1 | 12 | 10833.3333 | 66300 | -11508 | 0.8521 | 55466.6667 | 6.12 | Over Budget | Ahead of Schedule | In Progress | 1.2205
Project 93 | Healthcare IT | 270000 | 0.1 | 140941 | 6 | 20 | 81000 | 27000 | -113941 | 0.19157 | -54000 | 0.33333 | Over Budget | Behind Schedule | In Progress | 1.8829
Project 94 | GovTech | 95000 | 0.42 | 68445 | 3 | 12 | 23750 | 39900 | -28545 | 0.58295 | 16150 | 1.68 | Over Budget | Ahead of Schedule | In Progress | 2.0749
Project 95 | Clean Energy | 800000 | 0.89 | 722190 | 2 | 20 | 80000 | 712000 | -10190 | 0.98589 | 632000 | 8.9 | Over Budget | Ahead of Schedule | In Progress | 1.131
Project 96 | E-Commerce | 180000 | 0.94 | 152868 | 6 | 12 | 90000 | 169200 | 16332 | 1.1068 | 79200 | 1.88 | Under Budget | Ahead of Schedule | In Progress | 0.39805
Project 97 | FinTech | 350000 | 0.58 | 345879 | 7 | 20 | 122500 | 203000 | -142879 | 0.58691 | 80500 | 1.6571 | Over Budget | Ahead of Schedule | In Progress | 35.671
Project 98 | Cybersecurity | 110000 | 0.11 | 109703 | 6 | 12 | 55000 | 12100 | -97603 | 0.1103 | -42900 | 0.22 | Over Budget | Behind Schedule | In Progress | 329.6296
Project 99 | Healthcare IT | 1000000 | 0.28 | 448834 | 18 | 20 | 900000 | 280000 | -168834 | 0.62384 | -620000 | 0.31111 | Over Budget | Behind Schedule | In Progress | 1.3063
Project 100 | Cybersecurity | 60000 | 0.97 | 24792 | 2 | 6 | 20000 | 58200 | 33408 | 2.3475 | 38200 | 2.91 | Under Budget | Ahead of Schedule | In Progress | 0.051125

## Grading System
Business Sector | Average CPI | Average SPI | Budget Compliance | Budget Reserve Level | TCPI Compliance | Total Sector Score
E-Commerce | 1 | 1 | 0 | 0 | 1 | 3
Clean Energy | 1 | 1 | 1 | 1 | 0 | 4
EdTech | 1 | 1 | 1 | 1 | 1 | 5
Healthcare IT | 1 | 1 | 0 | 1 | 1 | 4
FinTech | 1 | 1 | 1 | 1 | 1 | 5
Enterprise Software | 0 | 1 | 0 | 1 | 1 | 3
GovTech | 1 | 1 | 0 | 1 | 1 | 4
Cybersecurity | 1 | 1 | 1 | 1 | 1 | 5
Artificial Intelligence | 0 | 0 | 0 | 0 | 1 | 1
Telecommunications | 1 | 1 | 1 | 1 | 1 | 5
Average CPI >.9
Average SPI > .75
Fewer Than 50 % Over Budget
Budget Reserve >= 30% of total budget
Average TCPI > .9
Each requirement is worth a single point on a 5 point scale
The sector grade is determined by their performance in this regard

## Averages
| Averge CPI | Average SPI | % Over Budget | % Under Budget | Sector Budget Reserve or Deficit | Sector Total Budget | Average TCPI
E-Commerce | 1.0298 | 1.6417 | 66.67% | 33.33% | 684659 | 2365000 | 5.9055
Clean Energy | 1.685 | 2.357 | 30% | 70% | 1270444 | 3080000 | 0.85608
EdTech | 4.0464 | 1.7923 | 31.25% | 68.75% | 1781056 | 3765000 | 1.7087
Healthcare IT | 4.8923 | 2.8936 | 63.64% | 36.36% | 2726151 | 5390000 | 1.5013
FinTech | 1.6981 | 1.5351 | 45.45% | 54.55% | 941947 | 2240000 | 6.0081
Enterprise Software | 0.79072 | 1.5751 | 71.43% | 28.57% | 1109802 | 2360000 | 6.9054
GovTech | 208.0615 | 3.6271 | 50% | 50% | 1731268 | 3445000 | 3.2047
Cybersecurity | 7.9074 | 1.5405 | 40% | 60% | 1533399 | 2495000 | 34.3263
Artificial Intelligence | 0.62083 | 0.59627 | 80% | 20% | 296223 | 1765000 | 22.0036
Telecommunications | 1.342 | 1.9157 | 42.86% | 57.14% | 851859 | 1995000 | 1.1462

## Grades
Business Sector | Performance Grade
E-Commerce | 3
Clean Energy | 4
EdTech | 5
Healthcare IT | 4
FinTech | 5
Enterprise Software | 3
GovTech | 4
Cybersecurity | 5
Artificial Intelligence | 1
Telecommunications | 5